## Risk_Register
PROJECT RISK REGISTER, FRAUD MITIGATION & EXCEPTION HANDLING
Risk ID | Risk Category | Risk Event & Root Cause | Probability | Impact | Risk Severity | Mitigation & Prevention Strategy (Business Rule) | Contingency / Fallback Plan | Risk Owner | Status
RSK-01 | Fraud & Abuse | Customers exploit 'Instant Doorstep Refund' by handing over used/counterfeit items or empty boxes to hurried couriers. | Medium | High | High | Enforce BR-06 (<=₹5,000 & Return Rate <35% only) + BR-08 mandatory 4-point mobile QC with barcode scan & tag photo. | Auto-block Green Channel for any account with 1 failed FC C-Returns audit; debit ATS Delivery Station / Associate for unverified scans. | Trust & Risk Lead | Mitigated
RSK-02 | Operational | 4-Point Doorstep QC increases courier stop time, causing daily delivery/pickup route delays. | Medium | Medium | Medium | Streamlined mobile UI to 4 binary taps + 1 barcode scan (benchmarked at 65 seconds per stop in pilot). | Disable doorstep photo step during peak Great Indian Festival (GIF) sale days for trusted Tier-1 accounts. | Reverse Logistics Head | Mitigated
RSK-03 | Financial / Promo | Customers game 'Buy X Get Y' or minimum-cart coupons by returning high-margin items and keeping discounted items. | High | Medium | High | Implement BR-05 deterministic Pro-Rata Coupon Recalculation engine shown upfront prior to return confirmation. | Waive promo clawback if customer chooses Store Exchange or Amazon Pay Balance credit. | CFO / Finance Lead | Mitigated
RSK-04 | Technical / Banking | NPCI UPI or IMPS banking network downtime causes Instant Refund or Penny-Drop timeouts. | Medium | Medium | Medium | Asynchronous retry queue with exponential backoff (every 15m for 4 hours) + multi-gateway routing (Amazon Pay UPI + NPCI / Axis-Yes Bank Payout Rails). | Send automated SMS offering 1-click switch to Instant Amazon Pay Balance (+5% bonus) if bank rails are down. | Payment Architect | Mitigated
RSK-05 | Customer Experience | Legitimate customer's return is wrongly rejected at doorstep by an untrained courier agent. | Medium | High | Medium | Require courier to capture clear photo of alleged defect/missing tag before the app allows 'QC Fail' submission. | Customer receives instant 'Contest Rejection' button in app -> Priority L2 Support review within 4 hours. | VP of CX | Mitigated
RSK-06 | Abuse of Policy | Customers systematically order <₹299 items and claim damage to get free 'Returnless Refunds'. | Low | Medium | Low | Enforce BR-09 hard cap of max 1 Returnless Refund per customer/device/address per 365 days + mandatory live camera photo. | Route any 2nd claim on <₹299 items to standard physical pickup. | Product Manager | Mitigated